## questions
date sent | # | RFP Question Category | Clarification Request from Vendor | JPS Response/ Clarification
2023-04-06 | 1 | Existing Network | Confirm if there is an existing network and provide existing equipment. | As this will be a stand-alone network, consider that there is no existing network
2023-04-06 | 2 | Decommissioning | Confirm if equipment and antenna decommision & removal is required for this project - and if so, which sites? Where should decommissioned equipment be deposited upon removal? | No. JPS will do all installations
2023-04-06 | 3 | Cutover | Confirm if cutover is required. Please provide details outlining preferred method. i.e. is there a maintenance window outside of standard business hours required for traffic cutover. | No. JPS will do all installations
2023-04-06 | 4 | Project phased over a three (3) year period | Please confirm if the intent is for a single award and single PO or in different phases. i.e. What purchasing method will be used by JPS? | Depending cost, the purchase may be split. The purchasing method is Purchase Order
2023-04-06 | 5 | Equipment Delivery | Please confirm delivery point and Incoterm preferred for delivery. | Both CIFKin and Exworks options
2023-04-06 | 7 | Training | Please confirm if Training should be in Jamaica, at the vendor facility, or virtually led by an instructor. | In Jamaica
2023-04-06 | 8 | Factory Testing and Pre-Configuration | Please confirm if JPS will be attending the Factory Acceptance Test in Austin, TX USA. | No
2023-04-06 | 9 | Capacity | Minimum throughput of 2 Mbps is identified, what is the expectation for Max throughput? | No expectations or limitations for Max throughput currently
2023-04-06 | 10 | Networking | The deployment of the network is in 3 phases; however, the G.8032 reslience will be designed and implemented for the complete system. How should the intermediate solution be handled for reslience for each phase? Does the existing network support STP, RSTP, or MSTP? Is JPS open to MW Vendor redefining the scope of each phase to encompass a ring for a more seamless ERPS deployment? | Deploy without ring protection N/A No
2023-04-06 | 11 | Interfaces | Is there a minimum quantity of interfaces required at each site for the DMR devices? | 1 interface, minimum
2023-04-06 | 12 | Avaialbility | Is the 99.999% availability a two-way or one-way requirement? And which method should be used for the availability calculation? i.e. ITU-T, Vigants-Barnett | All links are expected to meet the 99.999% availability
| 13 | Spectrum Availability | Within the 900 MHz spectrum range of frequencies for operation, does JPS have access to 100 MHz paired TX/RX channels with 9 MHz of separation between TX and RX for each RF paths requested in this RFP? | No
| 14 |  | Within the 900 MHz spectrum range of frequencies for operation, does JPS have access to 200 MHz paired TX/RX channels with 9 MHz of separation between TX and RX for each RF paths requested in this RFP? | No
| 15 |  | Will the vendor be responsible for spectrum acquisition? | No
| 16 | Mounting Questions | JPS states "All Outdoor mounting is preferred" in the mounting section. Is there a preference for the radio mounting at the base of the tower or co-located with the antenna? | Co-located with the antenna
| 17 |  | Is power available at the base of the tower? | No
| 18 |  | Is power available at any point on the tower above ground elevation? | No
| 19 |  | Is power available at the point on the tower where the antennae will be mounted? | No
| 20 |  | For outdoor mounting at either the base or anywhere on the tower, will a powered, control cabinet for the radio be provided by JPS? | No
| 21 | Networking Questions | Will a network switch be the termination point of the PTP radios? | Yes
| 22 |  | What is the make and model of the network switch at each tower location? | Cisco 4010
| 23 |  | For POE implementations, will JPS provide the network equipment required for the POE injection and data reception? (i.e., Network Switch) | Yes
| 24 |  | For networking, will the support OSPF be an option for JPS? | Yes
| 25 |  | Within JPS’s current network, what redundancy protocols are currently utilized? | STP and RSTP
| 26 | Hardware | As this is a new installation at each of the tower sites, do we need to include a separate 19” rack/cabinet and power supply for the equipment that will be mounted in the local transmission room? | No separate 19" rack/cabinet and power supply is required
| 27 | Spectrum Availability | As for frequency allowance to use for this project: Will JPS accept a network operating in the frequency of 1.4GHz (1350MHz to 1550 MHz) in channel sizes of 1.75MHz and aggregated up to 7.00MHz for larger capacity links in the future? | Yes, however, the availability will be determined by our Spectrum Management Authority
| 28 | Spectrum Availability | As for frequency allowance to use for this project: Will JPS accept a network operating in the frequency of 2GHz band (ITU fixed PtP accepted bands are, 2200MHz to 2290MHz) in channel sizes up to 1.75MHz? | Yes, however, the availability will be determined by our Spectrum Management Authority